## Slide 1
Day 48 of 60
FFIC Approvals on time
Project Update Dashboard – Government Approvals
Project Objective: Obtain govt. approvals for the required documents within the specified timeframe.
Project Time: The project began on April 1 and is currently on Day 48 out of 60 business days.
Project Risks:
Delays in task completion, particularly with Faz being out of town next week and additional budget overruns due to waiver fees and overtime.
Project Updates:
Completed items this week include: #220, 221, 224, 225, 226. However, #222 and 223 are still pending completion. Task #227 has just began, leading to a slight delay in progress for the week. The project has incurred and additional $6,200 over budget due to waiver fees and overtime. Karl is waiting an answer to a question regarding signatures.
Next Steps: Continue working on pending tasks and address any delays promptly. Monitor the budget closely and consider filling of extensions if necessary. Address Karl questions regarding sign promptly to prevent further delays.

## Slide 2
Iteration 4
Next Product Release: Tomorrow
Project Update Dashboard – Mobile App
Project Objective: Develop a mobile app
Project Time: The project is currently progressing smoothly, with prototypes developed and tasks completed ahead of schedule. Iteration 5 is set to begin soon indicating ongoing process and development.
Project Updates: Prototypes are developed and are under review. All planned tasks are completed and, there are no remaining items. Recent bugs in the app have been fixed, with positive feedback received from beta testers. The project is on track for release tomorrow pending review and acceptance of completed work.
Project Risks: With no immediate risks, ongoing monitoring of feedback and bug reports from beta testers to address any potential issues may arise post-release.
Project Next Steps: Review by product owner and team. Iteration 5 will release soon, with plans to expands user base and gather feedback.